## Gantt
TASK | Date | Days | Days Completed | %Complete | Status
Production Requirement & Analysis | 2024-02-07 | 10 | 10 | 100% | Done
Basic Architectural Design | 2024-02-16 | 7 | 7 | 100% | Done
Implementation(Coding) | 2024-02-23 | 9 | 9 | 100% | Done
Validation & Rework | 2024-03-03 | 14 | 14 | 100% | Done
Conceptulizaing Research Paper | 2024-03-17 | 15 | 15 | 100% | Done
Research Paper & Launching | 2024-04-01 | 20 | 7 | 35% | Working
Bug Fixing | 2024-04-21 | 6 | 0 | 0% | Not Started
Working
Not Started
Done